## AI Decision Log
Decision ID | Date | Decision Maker(s) | Decision Category | Context | Options Considered | Final Decision | Rationale | Impact | Attachments / Evidence | Status
DL-001 | 2025-01-10 | AI Program Manager | Risk Assessment | High-risk LLM use case submitted | Approve / Reject / Mitigate | Approve with mitigation | Mitigation reduces privacy risk | Medium | Risk Assessment v1.pdf | Closed
DL-002 | 2025-01-12 | AI Risk Manager | Security | Model vulnerable to prompt injection | Add filters / Train / Delay release | Add prompt filtering + adversarial testing | Chosen for security strengthening | High | ATLAS_Test_Results.pdf | Closed
DL-003 | 2025-01-15 | Data Protection Officer | Privacy | Sensitive data detected in training set | Mask / Remove / Aggregate | Remove & re-label dataset | Complies with PDPA/GDPR | High | Data_Audit.xlsx | Closed
DL-004 | 2025-01-18 | AI Program Manager | Model Change | New model version proposed | Deploy / Retrain / Delay | Retrain before deployment | Ensures fairness compliance | Medium | Model_Card_v2.docx | In Review
DL-005 | 2025-01-20 | AI Governance Board | Deployment | Approval for production release | Approve / Approve w/ guardrails | Approve with guardrails | Allows safe limited rollout | Low | Deployment_Readiness.pdf | Closed