## AI Audit Log
Audit ID | Date | Model Name | Issue Type | Severity | Description | Root Cause | Evidence | Action Taken | Owner | Status
AL-001 | 2025-01-05 | CreditRiskModel_v2 | Bias Spike | High | Model shows increased bias toward Group A | Training data imbalance | Bias_Audit_Report.pdf | Retrained with balanced dataset | AI Risk Manager | Closed
AL-002 | 2025-01-11 | ChatAssist_LLM | Hallucination Event | Medium | Model generated false factual information | Prompt sensitivity | Conversation_Log.txt | Added guardrails + retrieval layer | AI Program Manager | Monitoring
AL-003 | 2025-01-15 | FraudDetectionAI | Model Drift | High | Model accuracy dropped by 14% | Concept drift in new transactions | Performance_Metrics.xlsx | Triggered retraining cycle | ML Engineer | Closed
AL-004 | 2025-01-19 | GenAI_SummaryBot | Privacy Incident | High | LLM output included sensitive customer data | Insufficient anonymization | Privacy_Leak_Screenshot.png | Improved data masking pipeline | DPO | In Review
AL-005 | 2025-01-20 | ImageClassifier_v1 | Security Incident | Medium | Adversarial example bypassed classifier | Weak adversarial robustness | ATLAS_Test.png | Added adversarial training | Security Lead | Open